

**UK – Thailand**

**Capacity Building in Software and Hardware Infrastructures and Data Handling through Astronomy 2017**

**Case for Support**

This template should be completed using: Arial (or an equivalent) and a minimum font size of 11. A minimum of single line spacing and standard character spacing must be used. Margins must not be less than 2cm and the document must stay within the page lengths specified for each section.

1. **General Information**

**Project Title** *[up to 150 characters]*

|  |
| --- |
| Using astronomy surveys to train Thai researchers in handling Big Data |

**Theme**

*Please identify which themes your proposal covers:*

* Mechatronics/telescope control
* VLBI engineering, technology and research
* Data handling
* Outreach to support STEM education programme in schools

All projects should include some element of outreach activity.

|  |
| --- |
| Data handling |

1. **Previous track record of applicants and links between proposed partners**

*Please summarise how the UK and Thai partners will work together and any previous interactions or experience of working internationally and collaboratively. Please take into account track records of the applicants and institutions and provide details of any facilities that are required to undertake the project outside of the host institutions. [Maximum 1 side of A4]*

|  |
| --- |
| The Thai and UK researchers will collaborate to broaden and build upon the success of our previous Newton-funded project: “Using astronomy surveys to train Thai researchers in Big Data analysis”. During that first phase of the project, our multi-disciplinary team has collaborated closely to successfully train Thai graduate students in advanced data handling and analysis techniques, covering machine learning and database management. The UK and Thai astronomers’ access to and understanding of the subtleties of analysing extremely large datasets combined with the Thai data scientists’ knowledge of database design and machine learning techniques has fostered a highly productive multi-disciplinary training and research environment for the Thai graduate students involved in the project. The skills that the graduate students have acquired through involvement in the project are directly applicable to economic sectors outside astronomy such as information technology, medicine, finance, modern agriculture, security, etc  Here, we request funds to support the next phase of this project in which we will: (a) disseminate the knowledge and skills we have acquired to date through a series of practical workshops aimed at research staff and students based at NARIT and other Thai research institutes, (b) continue our successful graduate training programme in which students gain advanced data-handling techniques through cutting-edge research projects. The knowledge gained from these graduate research projects will be disseminated during practical workshops held in year 2 of funding. A key component of both these project goals will be the establishment of a data centre based in NARIT which will be used as a training aid for staff and students. **Can this actually be achieved? Explore the possibility of cloud-based systems such as AWS?**  **The workshop component:** Over the past nine months of the current funding the UK and Thai astronomers have gained an understanding of the strengths and limitations of the tools used by data scientists to organise and analyse data. Similarly, the Thai data scientists now have a thorough understanding of the large datasets of the type used by astronomers, and the challenges associated with extracting meaningful information from that data. This makes our team ideally suited to training other Thai staff and students (especially those based at NARIT, but also elsewhere) in handling and analysing large datasets. During 24 months of funding, our team (including the current students) will collaborate to organise two week-long practical workshops (one each summer) to be attended by up to 50 trainees each (see Section 3b for a description of the contents of the workshops). Afterwards, our team will provide support for attendees with queries they have with regards to, for example, setting up database systems at their own institute or performing automated analyses of their own data.  **The graduate research component:** During the first phase of the project, our team has collaborated on two main research areas (see Section 3a for more details): (a) assessing the ability of different machine learning-based systems to categorise false and true positive detections in astronomical images and (b) assessing the suitability of different database management systems to organise and deliver on request large amounts of astronomical data. This research has been carried-out by three Thai graduate students (2 masters students and 1 PhD student) under the primary supervision of Thai astronomers and data scientists, with further guidance on the details of the input data and system requirements from the UK astronomers. This guidance has been provided via effective use of Slack (a direct messaging app), teleconferencing (e.g., Skype) and two separate visits of the UK astronomers to Thailand. To date, these graduate research projects have used simulated data, which provides a stable dataset with which to test different database systems and machine learning algorithms. Our primary aim for the next phase is for current and forthcoming graduate students to research how well our systems scale to the demands of real data, and in particular to the resulting large data rates. |

1. **Official Development Assistance (ODA) compliance**

*Please provide a statement and* ***evidence explaining******how*** *your proposed research is compliant with Official Development Assistance (ODA) guidelines. Proposals must contribute towards the economic development and welfare of Thailand. For more information on ODA please refer to the* [*http://www.newtonfund.ac.uk/about/what-is-oda/*](http://www.newtonfund.ac.uk/about/what-is-oda/) *and* [*RCUK Newton Fund Guidance*](http://www.rcuk.ac.uk/documents/international/odaguidancercukspecific-pdf)*. Your ODA compliance will be assessed from this statement so please ensure you consider this in detail.* ***If your proposal is not considered ODA compliant it will be rejected.***

*[Maximum 1 A4 page]*

|  |
| --- |
| As an upper middle-income country, Thailand has already successfully tackled many of the greatest problems of developing countries, such as basic infrastructure development. Instead, the primary economic challenge that Thailand now faces is to develop into a high-income economy. The Thai government has recognised that a key means of achieving this is by training a highly skilled workforce able to compete internationally in high-value-added sectors that rely heavily on innovation (<http://bit.ly/2dWCZ01>), such as those listed in section one. Today, many of these sectors involve the collection of large amounts of digital data, whether in the form of customer information, patient medical records, information of crop growth, logistical information about a production line or distribution network, stock prices, etc. Many of these sectors have been earmarked by the Thai Board of Investment (BOI) as eligible for investment promotion (http://bit.ly/2djPB06). To successfully develop within these economically important sectors, it is vital that the Thai economy has access to home-grown talent trained in handling large amounts of digital data. The main objective of our project is to increase the skill level and experience of Thai workers and students in this important area. It thus satisfies the ODA’s guidelines of “promoting the economic development and welfare of developing countries as its main objective” and providing “educational services” [points 3 & 6 of “Official Development Assistance – RCUK Newton Fund Guidance”].  As the first phase of our project has already demonstrated, the students that are the focus of our training package become experts in advanced data handling, capable of teaching others such skills in their chosen post-graduation sectors. Indeed, our current graduate students will all teach at the practical workshops planned for this second phase. In this way, the project represents sustainable development. The short-term success of the project will be measured by the destination of the students on completion of the project and whether the learned skills are being successfully applied to develop the Thai economy. This information will be acquired by contacting the students six months after completion of the project. It will then be compiled by the partners and fed back to NARIT and STFC. The project will be considered a success if the students are using their acquired data handling skills in their chosen areas of work, and especially if they are teaching others these skills. In this respect, the project will investigate whether the training is effective in addressing Thailand’s economic development problems, thereby satisfying the ODA’s guideline of “researching the problems of developing countries” [point 5 of “Official Development Assistance – RCUK Newton Fund Guidance”].  The training our project provides will be delivered by the UK and Thai partners via official Thai agencies: NARIT and Mae Fah Luang. It thereby satisfies the ODA’s guideline of being “provided by official agencies, including state and local governments, or by their executive agencies” [point 3 of “Official Development Assistance – RCUK Newton Fund Guidance”]. |

1. **Detailed Research Information**
2. **Current landscape**

*Describe how the current priorities and challenges in Thailand and the UK will be addressed through this project demonstrating knowledge and understanding of past and current work in the subject area*

*[Maximum 1 side of A4].*

|  |
| --- |
| The main objective of our on-going project is to help address the challenge of developing Thailand from an upper-middle to a high-income economy through training in high-level data-handling skills. A secondary objective is the development of an automated data-handling pipeline to organise and analyse large amounts of astronomical survey data obtained by the Gravitational-wave Optical Transient Observatory (GOTO) on La Palma, Spain. GOTO is a major new observatory, funded by the UK Universities of Warwick, Sheffield, and Leicester, Monash University (Australia), NARIT (Thailand) and the Observatory of Armagh (UK) that is able to survey the entire northern sky roughly every week, producing vast amounts of data (~250 gigabytes per night) in the process. It was commissioned earlier this year, and so is already generating data for the project. To be effective, the GOTO collaboration must overcome the challenge of analysing this data in a fast, automated way. By combining the skills, experience and resources of the Thai and UK partners, our project meets both our main and secondary objectives in an effective and efficient manner.  As highlighted in section 1, over the past nine months of the current Newton funding our team has provided training-through-research in both machine learning (ML) and database management. For the ML component, it became clear early on in the project that the most pressing challenge was that the number of false positives in the data outnumbered the true positives by many hundreds-to-one. Such “unbalanced” data is problematic for traditional algorithms as they struggle to find the defining characteristics of the rare true sources, leading to low success rates (e.g., identifying <10% of true positives). To tackle this, one of our graduate students has been researching techniques to artificially boost the information available from the true positives and, in doing so, is obtaining significantly higher success rates (e.g., identifying >90% of true positives). A description of this work has recently been accepted in the peer-reviewed proceedings of the 10th International Conference on Machine Learning and Computing, at which the student has also been selected to give an oral presentation. To date, however, this research has been based on simulated data, so a key goal of the next phase is to research the applicability of our current techniques to real GOTO data.  For the database component, another of our graduate students has been researching the suitability of different data management systems (DMS) to store GOTO data. In addition to setting up our own relational database system (as used by SDSS), he has also been assessing the suitability of non-relational databases (as used extensively in tech industries), which offer greater flexibility and, potentially, speed benefits. Our student has set up and demonstrated the feasibility of both DMS on small networks based at Mae Fah Luang University. We now request funding to test the scalability of both systems for the size and delivery rate of GOTO data.  During the last nine months of current Newton funding, our team has demonstrated our effectiveness in training graduate students in advanced data handling techniques. This is in spite of the steep learning curve associated with the earliest stages of multi-disciplinary research. As such, our team is even better prepared to expand and continue this training into the second and third years of our project, for which we now request funding. |

1. **Description of proposed work**

*Please describe the research and partnership activities proposed. Please also identify any risks and mitigation strategies.*

*[Maximum 2 sides of A4]*

|  |
| --- |
| **1. Project synopsis**  As highlighted above, our team has proven our ability to train Thai graduate students in advanced data handling techniques by using large amounts of astronomical data as training sets. We now wish to use the experience and skills of our team (including students) to help train others through practical workshops, thereby broadening the overall impact of the project. Further, with the staff team members having overcome the steep learning curve associated with the early stages of multidisciplinary research, we will train another cohort of graduate research students with even greater efficiency. Here, we request funds to achieve these goals, thereby capitalizing on our experience and ensuring that our project has sustainable, long-term impact on Thailand’s continued economic growth.   1. **Achieving the project goals**   To maximise the impact of our training, our project will consist of two main components:   * two week-long practical workshops to be held in June/July of each year of funding (i.e., 2018 and 2019); * a series of 18-month research projects during which four Thai students (3 MSc, 1 PhD) will continue to research optimal techniques to organise and analyse large astronomical datasets.   The practical workshops will be attended by up to 50 staff and students based at various institutes, including NARIT. Part of their goal will be to teach the new cohort of graduate students the science background to the project and technical skills that will help them get started with their research projects. After their first year of research, these same students will contribute to the second practical workshop by sharing the knowledge and skills they have acquired over the past 12 months of research. Below, we describe in detail what will be covered in the practical workshops and the focus of the research projects. First, however, we provide some context with a brief description of GOTO and the challenges the research component will attempt to overcome.  *2.1 The GOTO project*  The primary science goal of GOTO is to identify transient optical sources that are the counterparts of gravitational-wave (GW) sources detected with the Laser Interferometer Gravitational-wave Observatory (LIGO). It can achieve this by rapidly scanning the large (~100 sq. deg) error circle of the GW detection as soon as it receives a trigger from LIGO. When not following-up GW triggers, GOTO conducts an all-sky survey. This survey mode is a critical aspect of the GOTO project, as it provides an up-to-date reference map against which the post-trigger observations can be compared to identify any transient sources that may be associated with the GW event. GOTO was commissioned earlier this year and, having recently undergone a hardware upgrade, is currently delivering data.  *2.2 GOTO’s Data Handling Challenge*  On a typical night of observations, GOTO will observe between five and ten million sources (predominantly stars and galaxies, but also asteroids, satellites, etc). All these sources must be detected, measured, categorised and the resulting information recorded. The detection and measurement stages are solved problems in astronomy, even for such large data rates as GOTO. By contrast, categorizing such large numbers of sources on short timescales presents a significant challenge to astronomers. With manual classification an impossibility on these scales, we must instead turn to ML-based classification algorithms. Further, while storing large amounts of data is now feasible in terms of cost, organising this data in such a way that it is easily accessible on sufficiently short timescales for automatic analysis represents another significant unsolved challenge for GOTO.  *2.3 The practical workshops*  *2.4 The research projects*  Our team has already made progress in this area by developing algorithms to discriminate between true and false transient sources in simulated GOTO data. However, this is only the first part of a much larger challenge. With GOTO now delivering data our students will research how to adapt their algorithms to handle the complications of real data, while to be really successful GOTO must be able classify different types of source (e.g., star, galaxy, supernova, neutron-neutron star merger) in order to prioritise follow-up observations.  Disseminate what we’ve already learned re: ML and databasing via a series of summer workshops.  Install database infrastructure on NARIT’s HPC; providing training on installation and use during the summer workshops (attended by who)?  For research projects:  ML: further research on imbalanced data, deep image-based deep learning  DB: query design and optimization |

1. **Human Participation**

*Please provide the following information* ***if your project involves any kind of human participation*** *(please note that this is a requirement of the call). Any human participation must abide by UK and Thailand standards whether it is taking place in the UK or Thailand. Failure to complete this section may result in your proposal being rejected. If the project does not involve humans, please write ‘Non applicable’:*

* *Please indicate* ***where*** *the recruitment of the human participants/ samples/ tissue will take place and the appropriate agreements.*
* ***Please identify any ethical or health and safety issues arising from any involvement of people, human samples or personal data in the research proposal. Please give details of how these will be addressed and any specific risks mitigated.***
* *Please explain how the proposed research will be carried out to a high ethical standard* ***and how the research will abide by relevant legal requirements in the UK and Thailand.***
* *Please indicate the ethical approvals and* ***research governance arrangements that*** *will be sought/ have been sought and will be in place ahead of starting the grant in both the* ***UK and Thailand****.**(This may include arrangements for supporting and providing expert ethics advice to researchers, should unanticipated ethics issues arise, throughout the lifecycle of the grant.)*
* *If you’re using human samples/tissue please also provide information on the following:*
* *That what is being supplied is suitable for the research being undertaken.*
* *That the quantity of tissue being supplied is suitable, but not excessive for achieving meaningful results.*

*[Maximum 1 side of A4]*

|  |
| --- |
| Not applicable |

1. **Justification of animal use (if applicable)**

*Sufficient information and justification regarding* ***any animal research proposed****, regardless of country, must be provided. Any use of animals must abide by UK and Thailand standards whether it is taking place in the UK or Thailand. If the project does not involve animal use, write ‘Non applicable’*

*Applications including the use of animals should fully justify the animal use, including the following.*

*A statement that:*

* *They will adhere to all relevant national and local regulatory systems in the UK and Thailand.*
* *They will follow the guidelines laid out in the* [*Responsibility in the use of animals in bioscience research document*](https://www.nc3rs.org.uk/sites/default/files/Responsibility%20in%20the%20use%20of%20animals%20in%20bioscience%20research%20-%20July%202015.pdf) *and ensure that work is carried out to UK standards.*
* *Before initiation of the proposed research work, appropriate approvals from Institutional and/or central animal ethics committees will be obtained for experimental protocols to be adopted in their projects from both the UK and* ***Thailand (this is a requirement regardless of where the research is taking place).*** *Successful proposals may be expected to provide copies of these permissions before funding is released.*

*Please also detail the following:*

* *Please indicate* ***where*** *the animal research will take place (UK or overseas) and through which funder the resources are being sought. Applicants should include confirmation that animal welfare standards at the UK and Thailand institutions meet the requirements outlined above.*
* *Justification of the choice of design and numbers of animals and interventions.*
* *Adequate information concerning methodological issues.*
* *Information on the planned procedures to minimise experimental bias (for example, randomisation protocols, blinding) should be outlined or an explanation included as to why such procedures are not appropriate.*
* *Power calculations.*
* *The rationale for the experimental design.*
* *Any additional information which was not included in the proposal document but which is pertinent to the animal research proposed and which the funders should be aware of.*

*[Maximum 1 side of A4]*

|  |
| --- |
| Not applicable |

1. **Work plan**

*Please provide a Gantt chart, or diagrammatic work plan, for the project including milestones [Maximum 1 side of A4]*

**Signed by the UK and Thailand Partner**

*Date UK PI*

*\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

*Date Thai PI*

*\_\_\_\_\_\_\_\_\_\_\_\_\_ \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_*

*Input more as needed*